## Timeline & Checklist
THEATRE MARKETING TIMELINE & CHECKLIST
Created by Jack Paterson | Password (unlok cells): JPTimeline
www.JackPatersonTheatre.com
12 weeks | 3 weeks
Copy and bios | Opening night invitations out
Any Other Artist Information | Postcards & Posters Distribution
Create Talking Points | Going.com, Yelp.com, etc Listings
Begin Press Releases | Newsletter 2 & Email Blast
Begin Building Trailer | Production Specific Snail Mail Out
Press Release 2
10 weeks
Preview Photo Shoot | 2 weeks
Start advertising design process (Web, Poster, Flyer, Print) | Rehearsal Photos 2 (if needed)
Trailer 2 (if possible)
Critic’s Follow-up invitation
8 weeks | Begin ongoing Social Media updates
Early Listings (Web & Print)
Press Release Drafts Done and Approved | 1 week
Web Design completed | Tech/ Dress Photos
Tumblr/ Twitter update | Film B Role
Build Facebook Page/ Event | Social Media Posts (Daily)
Newsletter 3
6 weeks
Ad Design completed and confirmed | Week of 1
Postcards Distribution 1 | Follow Up Critic’s Phone Calls
Trailer 1 completed | Social Media (Daily)
Facebook opened | Collate Press
Webpage uploaded | Trailer 2 (w quotes)
Newsletter 1 | Newsletter 4 (after Opening)
Tumblr/ Twitter update | Press Release (After Opening: Events or Something Exciting)
Press Release 1 (Articles push)
Critic Invitations Sent
Week of 2
5 weeks | Collate Press
Create opening night invitation | Newsletter (if needed)
Confirm invitation list & contacts | Ongoing Social Media
Press Release (if something exciting happens)
4 weeks
Rehearsal Photos 1
Event listings (Print & Web) | Week 3
Facebook/ Google Ads | Ongoing Social Media
Note on Events: Intended to service the local community; provide a platform for partnerships with other charities and organizations; provide material for ongoing marketing while provoking conversation regarding the play.
Special Thank You to the Second Wind Theatre and the linked blog post